## Sheet1
Time allocated | 42
Total Time Taken | 5
Time Left | 37
Day | Time (h) | What Was Achieved | Notes
2024-02-24 | 1 | Researched into a building like system for placing the battleships | Found useful video see youtbe saved folder Unity Content
2024-02-25 | 2 | Implemented the video | Errors have been found and implementation needs to be changed to fit with the structure of my game.
2024-02-26 | 2 | Started bug fixing and writing more functionality to fit my requirtements. Also fixed all of the ship prefabs and implemented a simple UI system. | Placing ships still glitchy. Think its to do with colliders.