## Sheet1
Time allocated | 42
Total Time Taken | 20.5
Time Left | 21.5
Day | Time (h) | What Was Achieved | Notes
2024-02-24 | 2 | Researched into a building like system for placing the battleships | Found useful video see youtbe saved folder Unity Content
2024-02-25 | 2 | Implemented the video | Errors have been found and implementation needs to be changed to fit with the structure of my game.
2024-02-26 | 2 | Started bug fixing and writing more functionality to fit my requirtements. Also fixed all of the ship prefabs and implemented a simple UI system. | Placing ships still glitchy. Think its to do with colliders.
2024-02-27 | 2 | Added main menu and options menu | Add animations to the camera move to look better.
2024-03-01 | 1.5 | Added arrows for easier building movement | Need to redo the detection of whether a ship can be built or not as it doesnt work as intended
2024-03-02 | 1 | Started recognition of whether ship is hit or missed | Have testing arrays at the minute need to combine with building to make the arrays custom
2024-03-13 | 1 | Began AI bot to play against | Need a lot more work to find neighbours and then get the link to the player action script to get the values of there ships
2024-03-14 | 3 | Added a bounding box for map. Fixed prefab sizes and hit boxes. Created dictionary for all tiles | Dictionary created. Need to create one for finding out where player ship placements are and then can link to attacking script.
2024-03-15 | 3 | Made list to record players ship positions. Made dictionary to record names and postions of all the players ships. Change the prefabs so they have referances to corners of tiles for later checks. Stopped the building section once all ships had been built. | All dictionarys functioning correctly. To do next is combining all of my work together and and seeing if I can run and hit a ship an it register a hit, using referance points and dictionarys
2024-03-19 | 3 | Linked all parts together. almost | Very difficult today had issues with the dictionaries almost linked just one small issue with the saving of the player ship pos and overwriting the dictionary. Removed the tile map stuff as decided to go with the arrow and dictionary based method I have already built due to the fact that the tile map wasnt working.